## Info
AGILE RISK REGISTER TEMPLATE
PROJECT | ERP Systems for Bike Company
PROJECT MANAGER | Team 11
Description | This template takes source from https://www.smartsheet.com/risk-register-templates The register contents are filled according to the current project conditions.
DATE OF LAST UPDATE | March 16 2021

## Agile Risk Register
RISK ID NO. | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION STRATEGY | ACTION | OWNER | REASSESSMENT DATE | KEYS
| Choose from the drop-down menu. | give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | What can be done to lower or eliminate the impact or probability? | Choose from the drop-down menu. | Who's responsible? | MM/DD/YYYY | RISK CLASS | LEVEL | ACTION
1 | Industrial Capabilities | The project team is not familiar with the technology used to develop the system. | The schedule is severely delayed due to slow progress in the development phase. | 4 | 1 | 4 | Use online resources to train team. Hire an experienced developer as a mentor to guide team and answer questions. | Mitigate | Developers | 2021-03-31 | Industrial Capabilities | 1 | Avoid
2 | Requirements | The requirements were not clearly understood. There was a mis-communication between the stakeholders (developer<->project owner). | The features implemented are not up to the expectations of the project owner, which results in significant delay. | 3 | 2 | 6 | Consult the project owner every step of the way. Bring prototypes to discuss the details of ambiguous requirements. | Avoid | Software Lead | 2021-03-31 | Requirements | 2 | Exploit
3 | Schedule | The planning for the sprint is poorly done. It under-estimates the time required to perform some tasks. | Tasks are not completed on schedule. | 3 | 2 | 6 | Constantly refer to the schedule and adjust if necessary. Communicate progress across team and keep everyone in the loop. | Mitigate | Developers | 2021-03-31 | Test and Evaluation | 3 | Transfer / Share
4 | Logistics | The documentation produced (architecture, risk management, testing) is unrealistic and does not anticipate issues encountered during the development phase. | Activities cannot continue as planned. A new plan is due and some objectives may no longer be satisfied. | 3 | 2 | 6 | Consult the project owner every step of the way. Have the scrum master monitor the work in progress. | Avoid | Developers | 2021-03-31 | Logistics | 4 | Mitigate
5 | Requirements | Users have passwords saved onto a database | Sensitive data for any and all users could be leaked | 4 | 1 | 4 | All passwords are encrypted before being saved into the database | Mitigate | Developers for Login | 2021-03-31 | Schedule | 5 | Accept with No Action
6 | Requirements | Users have an identifier in order for the client and service to know who is using it | Sensitive data for any and all users could be leaked | 2 | 1 | 2 | All identifiers are encrypted before being saved into the client's side | Mitigate | Developers for Login | 2021-03-31 | External Factors
7 | Test and Evaluation | Test quality is poor and does not really test the requirement. | Requirements are not verified | 4 | 3 | 12 | Assess test quality with tools such as Jacoco, PITest; correct or improve tests based on report generated. | Mitigate | Test Developers/Reviewers | 2021-03-31
8 | External Factors | Other course loads prevent full commitment to the development. | Tasks are not completed on schedule. | 3 | 3 | 9 | Enhance communication across groups; shift responsibility if necessary; re-distribute tasks among members with less workloads. | Mitigate | Developers | 2021-03-31

## Risk Reporting Matrix
RISK REGISTER SCALE | [6 empty] | Level | Likelihood | Probability of Occurrence
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25 | 5 | Nearly certain | ~90
| 4 | 4 | 8 | 12 | 16 | 20 | 4 | Very likely | ~70
| 3 | 3 | 6 | 9 | 12 | 15 | 3 | Likely | ~50
| 2 | 2 | 4 | 6 | 8 | 10 | 2 | Less likely | ~30
| 1 | 1 | 2 | 3 | 4 | 5 | 1 | Unlikely | ~10
|  | 1 | 2 | 3 | 4 | 5
I M P A C T
Level |  | 1 | 2 | 3 | 4 | 5
Technical Performance |  | Minimal or no impact | Low effect | Some effect | Major consequence | Project failure
Schedule |  |  | Delay < 1 sprint | Delay ~ 1 sprint | Cut down features | Project failure
Cost |  | - | - | - | - | -