## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Team 11 - ERP Solution | Kevin L. | 2021-01-13 | 2021-04-20 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2021-01-13 | 2021-02-03 | 21 | Complete
| Account Creation | User Type | Sunny D. & Kim H. | 1 | 2021-01-19 | 2021-01-24 | 6 | Complete | Current focus on a generic user with focus on administrative functionality.
| Login | User Type | Sunny D. & Kim H. | 1 | 2021-01-28 | 2021-01-28 | 1 | Complete | Allow generic login of any registered user. Role-based segregation will be done at a later Sprint.
| Sprint 2 |  |  |  | 2021-02-04 | 2021-02-24 | 21 | Complete
| Product Creation | Bike Type | Kevin L. | 2 | 2021-02-04 | 2021-02-24 | 21 | Complete
| Material Creation, Tracking, and Editing | Bike Type | Omar S. | 8 | 2021-02-04 | 2021-02-24 | 21 | Complete
| Create Material List | Subtask | Omar S. | 2 | 2021-02-18 | 2021-02-20 | 3 | Complete
| Edit Material List | Subtask | Omar S. | 2 | 2021-02-18 | 2021-02-20 | 3 | Complete
| Track Material List | Subtask | Omar S. | 2 | 2021-02-18 | 2021-02-20 | 3 | Complete
| Ordering Material List (UI) | Subtask | - | 2 | - | - | 0 | Delayed | Placed to next sprint
| Inventory Tracking | Bike Type | Sunny D. | 5 | 2021-02-04 | 2021-02-24 | 21 | Complete
| Define Product Inventory | Subtask | Isratnoor | 1 | 2021-02-14 | 2021-02-15 | 2 | Complete
| Define Parts Inventory | Subtask | Yu Xiang Z. | 1 | 2021-02-18 | 2021-02-20 | 3 | Complete
| Forecasting Parts & Products | Subtask | Sunny D. | 3 | - | - | 0 | Cancelled | Forecasting does not work when multiple vendors who are potentially sellling the same things are expected. Moved to E-mail Generation Story in a future sprint
| Progression Cycle for Orders | Subtask | Sunny D. | 2 | - | - | 0 | Cancelled | Enhancement that was added just in case all other tasks were finished early. Cancelled as it is not needed for this Sprint.
| Setup Preconfigured Parts | Subtask | Saebom S. | 1 | 2021-02-23 | 2021-02-23 | 1 | Complete
| Create Support for Vendors | Subtask | Sunny D. | 2 | 2021-02-22 | 2021-02-23 | 2 | Complete
| Products and Parts UI | Subtask | Kim H. | 5 | 2021-02-20 | 2021-02-21 | 2 | Complete
| Sprint 3 |  |  |  | 2021-02-25 | 2021-03-17 | 21 | In Progress
| Connect to Product Machinery | Automation | Yu Xiang Z. | 5 | 2021-02-25 | 2021-03-17 | 21 | In Progress
| Define Product Machinery | Subtask | - | 1
| Support Timing for Product Machinery | Subtask | - | 2 |  |  |  |  | Must be done after Define Product Machinery
| Product Machinery UI | Subtask | - | 2
| Define, Order and Track Raw Materials and Final Product | Bike Type | Shijun D. | 8 | 2021-02-25 | 2021-03-17 | 21 | In Progress | Responsible party will choose the representatives later
| Define Raw Materials | Subtask | - | 1
| Define Final Product | Subtask | - | 1 |  |  |  |  | Add support for custom Products (Made-to-Order)
| Order Custom Products | Subtask | - | 3 |  |  |  |  | Add support for made-to-order products
| Update Products, Parts, Materials | Subtask | - | 2 |  |  |  |  | Update products to have price
| Database Enhancements | Enhancements | Sunny Deng | 1 | 2021-02-25 | 2021-03-17 | 21 | In Progress
| Change ID Generation | Database | Sunny Deng | 1
| Sprint 2 Remainings | Subtasks | Kevin L. & Omar S. | 2 | 2021-02-25 | 2021-03-17 | 21 | In Progress
| Ordering Material List (UI) | Subtask | - | 2 |  |  |  | In Progress | Taken from Sprint 2

## Notes
Story Points | Follows the Fibonacci Sequence, up to 13
1 | Very small amount of work
2
3
5
8
13 | Largest expected amount of work
This was chosen based because of the large difference in points between a small and large tasks
It was also chosen in reference to the following website: https://www.lucidchart.com/blog/fibonacci-scale-for-agile-estimation

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt